## Sheet1
Date (week ending) | Segment | Task | Responsible | Done
Spiral 1
2011-01-14 | Hummingbird | Check RAM usage and timing of code | Zhenkai Z | x
2011-01-21 | Coordinated Sim w/ Faults
| Toolchain | Plant modeling language changes and model migration | Joe P
| Hummingbird | Check data flow paths and thrust | Zhenkai Z
2011-01-28 | Coordinated Sim w/ Faults
| Toolchain | Plant modeling Stage 1 changes and test
| Hummingbird | Check out gains | Zhenkai Z
Spiral 2
2011-02-04 | Coordinated Sim w/ Faults
| Toolchain |  | Joe P
| Hummingbird | Waypoint interface | Zhenkai Z
2011-02-11 | Coordinated Sim w/ Faults
| Toolchain | Updated scheduler ready for integration | Joe P
| Hummingbird | Closed trajectory tests (small) | Zhenkai Z
2011-02-18 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Closed trajectory tests (large) | Zhenkai Z
Spiral 3
2011-02-25 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Outdoor trajectory test (small) | Zhenkai Z
2011-03-04 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Outdoor trajectory test (medium) | Zhenkai Z
2011-03-11 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Outdoor trajectory test (large) | Zhenkai Z
Spiral 4
2011-03-18 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Two quadrotors - closed test, small trajectories | Zhenkai Z
2011-03-25 | Coordinated Sim w/ Faults
Toolchain
| Hummingbird | Two quadrotors - closed test, larger trajectories
2011-04-01 | Coordinated Sim w/ Faults
Toolchain
Hummingbird