## Sheet1
2/16/2009:
Category | Task | Subtask | Assigned To | Status | Notes
High Priority
Virtual Helicopter | Plant Discretization | Testing in Simulator | Joe P. | Model ready. | Discretized model needs testing in simulator.
|  | Symbolic approach | Joe P. | In progress. | Taking a class.
| Inner Loop Discretization | Check performance | Joe P. |  | Is float implementation fast enough?
|  | Fixed point coefficients | Joe P. | In progress | Joint resolution of LMI and other constraints.
|  | Validating Passivity | Nick K. | In progress | Using sector conditions.
| Waypoint controller | Collision avoidance
Robostix Code | SL/SF Code generator | Testing on helicopter | Joe P. | In progress
|  | Fixed basic type inference. | Harmon N. | Done | Tests pass. Seems to be working great.
| AVR Code Generator | Code templates | Zsolt L. | Done. | GPIO, ADC, UART, what else?
|  | Integration into language | Joe P. | In progress | Refactoring interpreter infrastructure.
|  | Writing interpreter | Joe P. | In progress | Using IL and templates to do interpreters.
Sim Remote Access | Lab Setup | External connection | Joe P. | Done. | VNC over SSH
|  | Power Mgmt. | Joe P. |  | Looking at alternatives
|  | Security | Joe P. |  | Need to talk to Eric abt. Connections out
|  | Scripts | Joe P. |  | Control power, etc… from VNC session.
|  | Sim Model Changes | Joe P. | Done. | xPC data without direct observation
Language Refinement | Error handlers | What errors do we handle? | Zsolt L.
Modeling error handlers
Error handler semantics
| Event Handlers | Design infrastructure
|  | Specify semantics |  |  | Priority, timeliness, etc…
Medium Priority
BIP analysis | Design language interface | Read papers
Semantic model for ESMoL
BIP Model for semantics
ESMoL elements
| Analysis | Capture analysis results
Represent results to user
TrueTime simulation | Design | What can we do with it? |  |  | Needs discussion.
Capturing platform effects
Tool integration design
| Code generator | TDMA schedule generation | Joe P. | In progress | Dimensionality issues (see next item).
|  | Fix handling of dimensions | Emeka E. |  | Needs testing.
|  | Need better abstraction | Emeka E. |  | Generational approach.
| Platform assignment | Design/Prototype | Joe P. | Done. | Spreadsheet interface.
|  | User interface for ESMoL |  |  | Need to write up a simple spec.
|  | Task allocation stuff. | Joe P. |  | Needs a few experiments.
Scheduler Interface | Scheduler testing | Need more/bigger test cases | Joe P.
|  | Wrapper scripts for testing. | Joe P. | Done
|  | Automated schedule checker | Joe P. |  | Needed to check latencies (and for testing).
Low Priority
Real Helicopters | Acquisition | Decide on buy vs. build | Nicholas K. | In progress | If we buy is it open enough? Made inquiries.
Order something
Lab Setup | Set up equipment | Set up build box. |  |  | One Win machine should do automated builds.
|  | Move lab to Centre Bldg. | Joe P. | Done
Language Refinement | Inference of messages | To be discussed
| Units consistency | Language update |  |  | Still odd spots -- remove unused attributes.
|  | Create single units library |  |  | Some parsing code exists.
| Semantics | Tool integration |  |  | How can we integrate tools cleanly?
| Requirements | Look @ PAMS work |  |  | Talk with Chris vanBuskirk
|  | Open source tool |  |  | OSEE is one alternative -- what else?
Project Organization | Split SLSF from ESMoL | Language changes | Joe P. |  | Tried UDM update and backed it out.
|  | Make sure it all works | Joe P. | In progress
|  | Retarget code generators | Harmon N. | Done | Tests all work -- changes in separate branch.
|  | Merge changes into trunk. | Joe P. | In progress | All changes build -- need to update transforms.
Packaging
| Deployable Release | Build clean machine image
Make tool installer
Things Done
Virtual Helicopter | Plant Discretization | Fixing CMU dynamics | Nicholas K. | Done | Library posted to Wiki
|  | Discrete model | Nicholas K. | Done | First version in svn.
|  | Communications Testing | Peter / Joe | Done | Still working with Mathworks on issues.
| FRODO Comms | Port FRODO to Gumstix | Peter V. | Done
| Inner Loop Discretization | Try SLSF codegen for loop | Nicholas K. | Done | Limited primitives, symbolic constants…
|  | SLSF codegen fixes | Harmon N. | Done
| Waypoint controller | Passive Controller | Nicholas K. | Done
|  | Trajectory generator | Nicholas K. | Done
| Build connectors | Ordering parts | Joe P. | Done
|  | Make cables | Peter / Joe | Done | Debug cable has issues. xPC has issues.
| Move Lab | Equipment to Centre Bldg. | Joe P. | Done
|  | Set up Gumstix/Robostix | Peter / Joe | Done
|  | Get everything building | Joe P. | Done
Robostix Code | Comms w/ Gumstix | Buffer design | Peter V. | Done | Working.
|  | Data transfer | Peter V. | Done
|  | Gumstix scheduler | Peter V. | Done
| Interface w/ simulator | Level converter | Peter V. | Done
|  | Connector | Peter V. | Done
TrueTime simulation | Code generator | Get up to speed on TrueTime | Nag M. | Done | Works for compass example.
|  | Deployment mapping | Nag M. | Done | M-files describing tasks, etc…
Scheduler Interface | Generate sched config | Transformation rules | Joe P. | Done
|  | Output templates | Joe P. | Done
|  | Integrate into GME | Joe P. | Done | Required patch by Tihamer/Daniel.
| Put schedule into model | Add elements to language | Joe P. | Done
|  | Import schedule | Joe P. | Done
Lab Setup | Cleaning/organizing | Moving things around | Paul P. | Done | Organizing
|  | Cleaning | ??? | Done | Corroded batteries, molded fridge.
| Set up equipment | Clean install of PCs. | Paul P. | Done
|  | Software tools on PCs. | Paul P. | Done